## TASK
task_code | status_code | wbs_id | task_name | start_date | end_date | resource_list | delete_record_flag
Activity ID | Activity Status | WBS Code | Activity Name | (*)Start | (*)Finish | (*)Resources | Delete This Row
A1000 | Not Started | CEE240F22 | NTP | 2022-11-06 | 2022-11-11 16:00
A1001 |  |  | submit shut down request for facilities
A1002 |  |  | demo ceilings GL 6.5, M.4
A1003 |  |  | erect temp barrier, GL 6.5, M.4
A1004 |  |  | demo exterior walls GL 5.7 M
A1005 |  |  | demo interior walls GL 5.7 - 7.1 M.4
A1006 |  |  | remove, salvage column covers, GL 7.1 M
A1007 |  |  | demo ceilings 1L 7.1, M.4
A1008 |  |  | remove, dispose 8" san. sewer GL 5.7 D.4
A1009 |  |  | erect temp barrier 1L M.4
A1010 |  |  | demo exterior walls 1L 5.7 M
A1011 |  |  | demo interior walls 1L 6.5 M.4
A1012 |  |  | remove, salvage column covers, GL 7.1 M
A1013 |  |  | remove, dispose 6" forced storm line GL 6.5 D.4 - M.4
A1014 |  |  | cut and cap 6" storm drain GL 5.7 M.4 - N
A1015 |  |  | raise ext. conduit into ceiling cavity GL 10.5 B
A1016 |  |  | verify location of underground utilities sub-GL, Sector B
A1017 |  |  | demo existing slab as needed sub-GL, Sector B
A1018 |  |  | excavate soil sub-GL, Sector B
A1019 |  |  | excavate elevator pit sub-GL, Sector B
A1020 |  |  | erect shoring, timber lagging sub-GL, Sector B
A1021 |  |  | install piles sub-GL, Sector B
A1022 |  |  | formwork, rebar, for pile caps sub-GL, Sector B
A1023 |  |  | install anchor and bolt connections to moment frame sub-GL, Sector B
A1024 |  |  | pour concrete, strip formwork for pile caps sub-GL, Sector B
A1025 |  |  | formwork for footing sub-GL, Sector B
A1026 |  |  | rebar, pour, strip footings GL, Sector B
A1027 |  |  | formwork for foundations sub-GL, Sector B
A1028 |  |  | lay pipes, conduits sub-GL, sector B
A1029 |  |  | subgrade preparation GL, Sector B
A1030 |  |  | vapor barrier GL, Sector B
A1031 |  |  | rebar connecting new foundations to (E) GL, Sector B
A1032 |  |  | MEP in deck GL, sector B
A1033 |  |  | rebar, pour, strip foundations GL, Sector B
A1034 |  |  | erect columns GL, Sector B
A1035 |  |  | erect beams GL, Sector B
A1036 |  |  | MEP in deck 1L, sector B
A1037 |  |  | erect steel deck 1L, Sector B
A1038 |  |  | erect concrete deck 1L, Sector B
A1039 |  |  | erect columns 1L, Sector B
A1040 |  |  | erect beams 1L, Sector B
A1041 |  |  | MEP in deck 2L, sector B
A1042 |  |  | erect steel deck 2L, Sector B
A1043 |  |  | erect concrete deck 2L, Sector B
A1044 |  |  | erect columns 2L, Sector B
A1045 |  |  | erect steel deck 3L, Sector B
A1046 |  |  | curtain wall GL, Sector B
A1047 |  |  | curtain wall 1L, Sector B
A1048 |  |  | curtain wall 2L, Sector B
A1049 |  |  | erect temp barrier, west of new main connector, GL, Sector B
A1050 |  |  | erect temp barrier, west of new main connector, 1L, Sector B
A1051 |  |  | erect temp barrier, west of new main connector, 2L, Sector B
A1052 |  |  | remove roof assembly 2L (E)
A1053 |  |  | remove parapet, coping 2L (E)
A1054 |  |  | erect construction barrier 2L (E)
A1055 |  |  | remove ext window 2L (E)
A1056 |  |  | demo part of exterior wall 2L (E)

## TASKPRED
pred_proj_id | proj_id | PREDTASK__PROJWBS__wbs_full_name | TASK__PROJWBS__wbs_full_name | pred_task_id | task_id | PREDTASK__task_name | TASK__task_name | pred_type | lag_hr_cnt | PREDTASK__status_code | TASK__status_code | PREDTASK__rsrc_id | TASK__rsrc_id | delete_record_flag
(*)Predecessor Project | (*)Successor Project | (*)Predecessor WBS | (*)Successor WBS | Predecessor | Successor | (*)Predecessor Activity Name | (*)Successor Activity Name | Relationship Type | Lag | (*)Predecessor Activity Status | (*)Successor Activity Status | (*)Predecessor Primary Resource | (*)Successor Primary Resource | Delete This Row

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Hour ShowAsPercentage=0 SmallScaleQtyType=QT_Hour DateFormat=M/d/yyyy CurrencyFormat=US Dollar