## cee240_sched_activities_numbere
Copy of Full Schedule
Increment 1, Sector B (Lev G,1,2): Demo, Superstructure, Building Envelope
lay pipes, conduits sub-GL, sector B | 25.1
submit shut down request for facilities | 1
erect temp barrier, GL 6.5, M.4 | 3
MEP in deck GL, sector B | 29
MEP in deck 1L, sector B | 33
MEP in deck 2L, sector B | 38
erect temp barrier, west of new main connector, GL, Sector B | 46
remove roof assembly 2L (E) | 49
remove parapet, coping 2L (E) | 50
erect construction barrier 2L (E) | 51
remove ext window 2L (E) | 52
demo part of exterior wall 2L (E) | 53
NTP | 0
demo ceilings GL 6.5, M.4 | 2
demo exterior walls GL 5.7 M | 4
demo interior walls GL 5.7 - 7.1 M.4 | 5
remove, salvage column covers, GL 7.1 M | 6
remove, dispose 8" san. sewer GL 5.7 D.4 | 7
remove, dispose 6" forced storm line GL 6.5 D.4 - M.4 | 12
cut and cap 6" storm drain GL 5.7 M.4 - N | 13
raise ext. conduit into ceiling cavity GL 10.5 B | 14
verify location of underground utilities sub-GL, Sector B | 15
demo existing slab as needed sub-GL, Sector B | 16
excavate soil sub-GL, Sector B | 17
excavate elevator pit sub-GL, Sector B | 18
erect shoring, timber lagging sub-GL, Sector B | 19
install piles sub-GL, Sector B | 20
formwork, rebar, for pile caps sub-GL, Sector B | 21
install anchor and bolt connections to moment frame sub-GL, Sector B | 22
pour concrete, strip formwork for pile caps sub-GL, Sector B | 23
rebar, pour, strip footings GL, Sector B | 24
formwork for foundations sub-GL, Sector B | 25
subgrade preparation GL, Sector B | 26
vapor barrier GL, Sector B | 27
rebar connecting new foundations to (E) GL, Sector B | 28
rebar, pour, strip foundations GL, Sector B | 30
erect columns GL, Sector B | 31
erect beams GL, Sector B | 32
erect steel deck 1L, Sector B | 34
erect concrete deck 1L, Sector B | 35
erect columns 1L, Sector B | 36
erect beams 1L, Sector B | 37
erect steel deck 2L, Sector B | 39
erect concrete deck 2L, Sector B | 40
erect columns 2L, Sector B | 41
erect steel deck 3L, Sector B | 42
curtain wall GL, Sector B | 43
erect temp barrier, west of new main connector, 1L, Sector B | 47
curtain wall 1L, Sector B | 44
formwork for footing sub-GL, Sector B | 23.1
erect temp barrier, west of new main connector, 2L, Sector B | 48
curtain wall 2L, Sector B | 45
demo ceilings 1L 7.1, M.4 | 7
erect temp barrier 1L M.4 | 8
demo exterior walls 1L 5.7 M | 9
demo interior walls 1L 6.5 M.4 | 10
remove, salvage column covers, GL 7.1 M | 11
Increment 2, Phase 1: Interior Build Out | -
Sector B (Lev G) | -
rough in ceiling MEP work GL, sector B | 8
install interior non-rated partitions GL, Sector B | 9
finish MEP work GL, sector B | 10
install flooring GL, Sector B | 11
install SDA GL, Sector B | 12
erect ceiling in connector area GL, Sector B | 13
install underslung elevator GL, Sector B | 14
install column covers in connector area GL, Sector B | 15
re-install column covers GL, Sector B | 16
re-install roll down door with egress GL, Sector B | 17
install doors at storage GL, Sector B | 18
remove temp barrier GL, Sector B | 19
perform patching work as needed GL, Sector B | 20
paint walls GL, Sector B | 21
install floor finishes GL, Sector B | 22
install ceilings finishes GL, Sector B | 23
testing and commissioning GL, Sector B | 24
erect temp barrier GL, Sector B | 0 | --
demo interior barrier GL, Sector B | 1
demo ceiling entirely GL, Sector B | 4
install seismic joints GL, Sector B | 5
erect interior barriers GL, Sector B | 6
rough in wall MEP work GL, sector B | 7
plaster walls GL, Sector B | 12.1
demo DDA GL, Sector B | 2
relocate DDA to other side of room GL, Sector B | 3
Sector B (Lev 1) | -
rough in ceiling MEP work 1L, sector B | 8
install interior partitions 1L, Sector B | 9
install flooring at spec. locations 1L, Sector B | 10
finish MEP work 1L, sector B | 12
install underslung elevator 1L, Sector B | 13
testing and commissioning 1L, Sector B | 24
erect temp barrier 1L, Sector B | 0
erect interim construction tunnel 1L, Sector B | 1
demo interior fire barrier, DDA 1L, Sector B | 2
demo interior partitions 1L, Sector B | 3
install seismic joints 1L, Sector B | 4
remove, salvage door for meditation room 1L, Sector B | 5
remove, salvage column covers 1L, Sector B | 6
rough in wall MEP work 1L, sector B | 7
install cieling at spec. locations 1L, Sector B | 11
install column covers in connector area 1L, Sector B | 14
install roll down door with egress 1L, Sector B | 15
replace mediation room door 1L, Sector B | 16
remove temp barriers and tunnel 1L, Sector B | 17
remove temp barrier 1L, Sector B | 18
perform patching work as needed 1L, Sector B | 19
plaster walls 1L, Sector B | 20
paint walls 1L, Sector B | 21
install floor finishes 1L, Sector B | 22
install ceiling finishes 1L, Sector B | 23
Sector B (Lev 2)
testing and commissioning 1L, Sector B | 17
erect int. 2hr partitions 2L, Sector A | 0
erect int. 1hr partitions 2L, Sector A | 1
erect int. non-rated partitions 2L, Sector A | 2
rough in ceiling MEP work 2L, sector A | 3
rough in wall MEP work 2L, sector A | 4
install flooring at spec. locations 2L, Sector A | 5
finish MEP work 2L, sector A | 6
erect ceilings in elevator lobby 2L, Sector A | 7
install underslung elevator 2L, Sector A | 8
install column covers in connector area 2L, Sector A | 9
install DDA between IMOB and elevator 2L, Sector A | 10
remove temp barrier 2L, Sector A | 11
perform patching work as needed 2L, Sector A | 12
plaster walls 2L, Sector A | 13
paint walls 2L, Sector A | 14
install floor finishes 2L, Sector A | 15
install ceiling finishes 2L, Sector A | 16
Sector A (Lev G)
demo ext. walls at IMOB connection GL, Sector A | 2
demo all ceilings, salvage lights GL, Sector A | 3
install seismic joints GL, Sector A | 4
rough in wall MEP work GL, sector A | 5
remove temp barrier GL, Sector A | 10
perform patching work as needed GL, Sector A | 11
erect temp barrier GL, Sector A | 0
install ext. DDA GL, Sector A | 1
rough in ceiling MEP work GL, sector A | 6
install interior non-rated partitions GL, Sector A | 7
finish MEP work GL, sector A | 8
replace light fixtures 1L, Sector A | 9
plaster walls GL, Sector A | 12
paint walls GL, Sector A | 13
install floor finishes GL, Sector A | 14
install ceiling finishes GL, Sector A | 15
testing and commissioning GL, Sector A | 16
Sector A (Lev 1) needs to be after sector b
rough in ceiling MEP work 1L, sector A | 6
install interior non-rated partitions, door 1L, Sector A | 7
finish MEP work 1L, sector A | 8
install equipment, casework 1L, Sector A | 9
install side coiling security door 1L, Sector A | 10
erect ceilings 1L, Sector A | 12
replace light fixtures 1L, Sector A | 13
create opening at south exterior side of wall 1L, Sector A | 14
install roll down door with egress 1L, Sector A | 15
remove temp barrier 1L, Sector A | 16
perform patching work as needed 1L, Sector A | 17
erect temp barrier 1L, Sector A | 0
remove, salvage column covers 1L, Sector A | 1
demo interior partitions and SDA 1L, Sector A | 2
demo all ceilings, salvage lights 1L, Sector A | 3
install seismic joints GL, Sector A | 4
rough in wall MEP work 1L, sector A | 5
reinstall column covers 1L, Sector A | 11
Increment 2, Phase 2: Interior Build Out
Sector A (Lev 1)
wait until New Main Connector occupancy 1L, Sector A | 0
wait until proposed IMOB occupancy 1L, Sector A | 1
erect temp barrier 1L, Sector A | 2
demo 2hr partition and DDA 1L, Sector A | 3
rough in MEP work GL, sector A | 4
erect interior partitions and SDA 1L, Sector A | 5
finish MEP work GL, sector A | 6
install ceilings 1L, Sector A | 7
remove temp barriers 1L, Sector A | 8
perform patching work as needed 1L, Sector A | 9
plaster walls 1L, Sector A | 10
paint walls 1L, Sector A | 11
install floor finishes 1L, Sector A | 12
install cieling finsihes 1L, Sector A | 13
testing and commissioning 1L, Sector A | 14
Courtyard
install trees Courtyard | 0
install concrete paving Courtyard | 1
install light fixtures Courtyard | 3
install courtyard furnishings Courtyard | 5
protect trees Courtyard | 2
install resin paving Courtyard | 4