## ordered_act_dur
| activities | index | act_ordered | durations
0 | lay pipes, conduits sub-GL, sector B | 25.1 | NTP | 0
1 | submit shut down request for facilities | 1 | submit shut down request for facilities | 1
2 | erect temp barrier, GL 6.5, M.4 | 3 | demo ceilings GL 6.5, M.4 | 2
3 | MEP in deck GL, sector B | 29 | erect temp barrier, GL 6.5, M.4 | 3
4 | MEP in deck 1L, sector B | 33 | demo exterior walls GL 5.7 M | 3
5 | MEP in deck 2L, sector B | 38 | demo interior walls GL 5.7 - 7.1 M.4 | 3
6 | erect temp barrier, west of new main connector, GL, Sector B | 46 | remove, salvage column covers, GL 7.1 M | 1
7 | remove roof assembly 2L (E) | 49 | demo ceilings 1L 7.1, M.4 | 2
8 | remove parapet, coping 2L (E) | 50 | remove, dispose 8" san. sewer GL 5.7 D.4 | 3
9 | erect construction barrier 2L (E) | 51 | erect temp barrier 1L M.4 | 3
10 | remove ext window 2L (E) | 52 | demo exterior walls 1L 5.7 M | 3
11 | demo part of exterior wall 2L (E) | 53 | demo interior walls 1L 6.5 M.4 | 1
12 | NTP | 0 | remove, salvage column covers, GL 7.1 M | 3
13 | demo ceilings GL 6.5, M.4 | 2 | remove, dispose 6" forced storm line GL 6.5 D.4 - M.4 | 3
14 | demo exterior walls GL 5.7 M | 4 | cut and cap 6" storm drain GL 5.7 M.4 - N | 1
15 | demo interior walls GL 5.7 - 7.1 M.4 | 5 | raise ext. conduit into ceiling cavity GL 10.5 B | 3
16 | remove, salvage column covers, GL 7.1 M | 6 | verify location of underground utilities sub-GL, Sector B | 1
17 | remove, dispose 8" san. sewer GL 5.7 D.4 | 7 | demo existing slab as needed sub-GL, Sector B | 2
18 | remove, dispose 6" forced storm line GL 6.5 D.4 - M.4 | 12 | excavate soil sub-GL, Sector B | 2
19 | cut and cap 6" storm drain GL 5.7 M.4 - N | 13 | excavate elevator pit sub-GL, Sector B | 1
20 | raise ext. conduit into ceiling cavity GL 10.5 B | 14 | erect shoring, timber lagging sub-GL, Sector B | 4
21 | verify location of underground utilities sub-GL, Sector B | 15 | install piles sub-GL, Sector B | 4
22 | demo existing slab as needed sub-GL, Sector B | 16 | formwork, rebar, for pile caps sub-GL, Sector B | 8
23 | excavate soil sub-GL, Sector B | 17 | install anchor and bolt connections to moment frame sub-GL, Sector B | 2
24 | excavate elevator pit sub-GL, Sector B | 18 | pour concrete, strip formwork for pile caps sub-GL, Sector B | 12
25 | erect shoring, timber lagging sub-GL, Sector B | 19 | formwork for footing sub-GL, Sector B | 2
26 | install piles sub-GL, Sector B | 20 | rebar, pour, strip footings GL, Sector B | 10
27 | formwork, rebar, for pile caps sub-GL, Sector B | 21 | formwork for foundations sub-GL, Sector B | 2
28 | install anchor and bolt connections to moment frame sub-GL, Sector B | 22 | lay pipes, conduits sub-GL, sector B | 5
29 | pour concrete, strip formwork for pile caps sub-GL, Sector B | 23 | subgrade preparation GL, Sector B | 2
30 | rebar, pour, strip footings GL, Sector B | 24 | vapor barrier GL, Sector B | 4
31 | formwork for foundations sub-GL, Sector B | 25 | rebar connecting new foundations to (E) GL, Sector B | 4
32 | subgrade preparation GL, Sector B | 26 | MEP in deck GL, sector B | 3
33 | vapor barrier GL, Sector B | 27 | rebar, pour, strip foundations GL, Sector B | 10
34 | rebar connecting new foundations to (E) GL, Sector B | 28 | erect columns GL, Sector B | 4
35 | rebar, pour, strip foundations GL, Sector B | 30 | erect beams GL, Sector B | 4
36 | erect columns GL, Sector B | 31 | MEP in deck 1L, sector B | 3
37 | erect beams GL, Sector B | 32 | erect steel deck 1L, Sector B | 4
38 | erect steel deck 1L, Sector B | 34 | erect concrete deck 1L, Sector B | 4
39 | erect concrete deck 1L, Sector B | 35 | erect columns 1L, Sector B | 4
40 | erect columns 1L, Sector B | 36 | erect beams 1L, Sector B | 4
41 | erect beams 1L, Sector B | 37 | MEP in deck 2L, sector B | 3
42 | erect steel deck 2L, Sector B | 39 | erect steel deck 2L, Sector B | 4
43 | erect concrete deck 2L, Sector B | 40 | erect concrete deck 2L, Sector B | 4
44 | erect columns 2L, Sector B | 41 | erect columns 2L, Sector B | 4
45 | erect steel deck 3L, Sector B | 42 | erect steel deck 3L, Sector B | 4
46 | curtain wall GL, Sector B | 43 | curtain wall GL, Sector B | 15
47 | erect temp barrier, west of new main connector, 1L, Sector B | 47 | curtain wall 1L, Sector B | 15
48 | curtain wall 1L, Sector B | 44 | curtain wall 2L, Sector B | 15
49 | formwork for footing sub-GL, Sector B | 23.1 | erect temp barrier, west of new main connector, GL, Sector B | 3
50 | erect temp barrier, west of new main connector, 2L, Sector B | 48 | erect temp barrier, west of new main connector, 1L, Sector B | 3
51 | curtain wall 2L, Sector B | 45 | erect temp barrier, west of new main connector, 2L, Sector B | 3
52 | demo ceilings 1L 7.1, M.4 | 7 | remove roof assembly 2L (E) | 5
53 | erect temp barrier 1L M.4 | 8 | remove parapet, coping 2L (E) | 5
54 | demo exterior walls 1L 5.7 M | 9 | erect construction barrier 2L (E) | 3
55 | demo interior walls 1L 6.5 M.4 | 10 | remove ext window 2L (E) | 5
56 | remove, salvage column covers, GL 7.1 M | 11 | demo part of exterior wall 2L (E) | 5
nc | Increment 2, Phase 1: Interior Build Out | -
58 | Sector B (Lev G) | -
59 | rough in ceiling MEP work GL, sector B | 8 | erect temp barrier GL, Sector B | 3
60 | install interior non-rated partitions GL, Sector B | 9 | demo interior barrier GL, Sector B | 2
61 | finish MEP work GL, sector B | 10 | demo DDA GL, Sector B | 2
62 | install flooring GL, Sector B | 11 | relocate DDA to other side of room GL, Sector B | 2
63 | install SDA GL, Sector B | 12 | demo ceiling entirely GL, Sector B | 2
64 | erect ceiling in connector area GL, Sector B | 13 | install seismic joints GL, Sector B | 5
65 | install underslung elevator GL, Sector B | 14 | erect interior barriers GL, Sector B | 5
66 | install column covers in connector area GL, Sector B | 15 | rough in wall MEP work GL, sector B | 5
67 | re-install column covers GL, Sector B | 16 | rough in ceiling MEP work GL, sector B | 5
68 | re-install roll down door with egress GL, Sector B | 17 | install interior non-rated partitions GL, Sector B | 5
69 | install doors at storage GL, Sector B | 18 | finish MEP work GL, sector B | 10
70 | remove temp barrier GL, Sector B | 19 | install flooring GL, Sector B | 5
71 | perform patching work as needed GL, Sector B | 20 | install SDA GL, Sector B | 3
72 | paint walls GL, Sector B | 21 | plaster walls GL, Sector B | 5
73 | install floor finishes GL, Sector B | 22 | erect ceiling in connector area GL, Sector B | 10
74 | install ceilings finishes GL, Sector B | 23 | install underslung elevator GL, Sector B | 10
75 | testing and commissioning GL, Sector B | 24 | install column covers in connector area GL, Sector B | 3
76 | erect temp barrier GL, Sector B | 0 | re-install column covers GL, Sector B | 3
77 | demo interior barrier GL, Sector B | 1 | re-install roll down door with egress GL, Sector B | 3
78 | demo ceiling entirely GL, Sector B | 4 | install doors at storage GL, Sector B | 2
79 | install seismic joints GL, Sector B | 5 | remove temp barrier GL, Sector B | 2
80 | erect interior barriers GL, Sector B | 6 | perform patching work as needed GL, Sector B | 2
81 | rough in wall MEP work GL, sector B | 7 | paint walls GL, Sector B | 5
82 | plaster walls GL, Sector B | 12.1 | install floor finishes GL, Sector B | 5
83 | demo DDA GL, Sector B | 2 | install ceilings finishes GL, Sector B | 5
84 | relocate DDA to other side of room GL, Sector B | 3 | testing and commissioning GL, Sector B | 3
85 | Sector B (Lev 1) | -
86 | rough in ceiling MEP work 1L, sector B | 8 | erect temp barrier 1L, Sector B | 3
87 | install interior partitions 1L, Sector B | 9 | erect interim construction tunnel 1L, Sector B | 10
88 | install flooring at spec. locations 1L, Sector B | 10 | demo interior fire barrier, DDA 1L, Sector B | 2
89 | finish MEP work 1L, sector B | 12 | demo interior partitions 1L, Sector B | 2
90 | install underslung elevator 1L, Sector B | 13 | install seismic joints 1L, Sector B | 5
91 | testing and commissioning 1L, Sector B | 24 | remove, salvage door for meditation room 1L, Sector B | 1
92 | erect temp barrier 1L, Sector B | 0 | remove, salvage column covers 1L, Sector B | 1
93 | erect interim construction tunnel 1L, Sector B | 1 | rough in wall MEP work 1L, sector B | 5
94 | demo interior fire barrier, DDA 1L, Sector B | 2 | rough in ceiling MEP work 1L, sector B | 5
95 | demo interior partitions 1L, Sector B | 3 | install interior partitions 1L, Sector B | 5
96 | install seismic joints 1L, Sector B | 4 | install flooring at spec. locations 1L, Sector B | 5
97 | remove, salvage door for meditation room 1L, Sector B | 5 | install cieling at spec. locations 1L, Sector B | 5
98 | remove, salvage column covers 1L, Sector B | 6 | finish MEP work 1L, sector B | 10
99 | rough in wall MEP work 1L, sector B | 7 | install underslung elevator 1L, Sector B | 10
100 | install cieling at spec. locations 1L, Sector B | 11 | install column covers in connector area 1L, Sector B | 5
101 | install column covers in connector area 1L, Sector B | 14 | install roll down door with egress 1L, Sector B | 5
102 | install roll down door with egress 1L, Sector B | 15 | replace mediation room door 1L, Sector B | 1
103 | replace mediation room door 1L, Sector B | 16 | remove temp barriers and tunnel 1L, Sector B | 2
104 | remove temp barriers and tunnel 1L, Sector B | 17 | remove temp barrier 1L, Sector B | 2
105 | remove temp barrier 1L, Sector B | 18 | perform patching work as needed 1L, Sector B | 2
106 | perform patching work as needed 1L, Sector B | 19 | plaster walls 1L, Sector B | 5
107 | plaster walls 1L, Sector B | 20 | paint walls 1L, Sector B | 5
108 | paint walls 1L, Sector B | 21 | install floor finishes 1L, Sector B | 5
109 | install floor finishes 1L, Sector B | 22 | install ceiling finishes 1L, Sector B | 5
110 | install ceiling finishes 1L, Sector B | 23 | testing and commissioning 1L, Sector B | 3
111 | Sector B (Lev 2)
112 | testing and commissioning 1L, Sector B | 17 | erect int. 2hr partitions 2L, Sector A | 3
113 | erect int. 2hr partitions 2L, Sector A | 0 | erect int. 1hr partitions 2L, Sector A | 3
114 | erect int. 1hr partitions 2L, Sector A | 1 | erect int. non-rated partitions 2L, Sector A | 3
115 | erect int. non-rated partitions 2L, Sector A | 2 | rough in ceiling MEP work 2L, sector A | 5
116 | rough in ceiling MEP work 2L, sector A | 3 | rough in wall MEP work 2L, sector A | 5
117 | rough in wall MEP work 2L, sector A | 4 | install flooring at spec. locations 2L, Sector A | 5
118 | install flooring at spec. locations 2L, Sector A | 5 | finish MEP work 2L, sector A | 5
119 | finish MEP work 2L, sector A | 6 | erect ceilings in elevator lobby 2L, Sector A | 5
120 | erect ceilings in elevator lobby 2L, Sector A | 7 | install underslung elevator 2L, Sector A | 10
121 | install underslung elevator 2L, Sector A | 8 | install column covers in connector area 2L, Sector A | 5
122 | install column covers in connector area 2L, Sector A | 9 | install DDA between IMOB and elevator 2L, Sector A | 5
123 | install DDA between IMOB and elevator 2L, Sector A | 10 | remove temp barrier 2L, Sector A | 2
124 | remove temp barrier 2L, Sector A | 11 | perform patching work as needed 2L, Sector A | 2
125 | perform patching work as needed 2L, Sector A | 12 | plaster walls 2L, Sector A | 5
126 | plaster walls 2L, Sector A | 13 | paint walls 2L, Sector A | 5
127 | paint walls 2L, Sector A | 14 | install floor finishes 2L, Sector A | 5
128 | install floor finishes 2L, Sector A | 15 | install ceiling finishes 2L, Sector A | 5
129 | install ceiling finishes 2L, Sector A | 16 | testing and commissioning 1L, Sector B | 3
130 | Sector A (Lev G)
131 | demo ext. walls at IMOB connection GL, Sector A | 2 | erect temp barrier GL, Sector A | 3
132 | demo all ceilings, salvage lights GL, Sector A | 3 | install ext. DDA GL, Sector A | 3
133 | install seismic joints GL, Sector A | 4 | demo ext. walls at IMOB connection GL, Sector A | 3
134 | rough in wall MEP work GL, sector A | 5 | demo all ceilings, salvage lights GL, Sector A | 3
135 | remove temp barrier GL, Sector A | 10 | install seismic joints GL, Sector A | 5
136 | perform patching work as needed GL, Sector A | 11 | rough in wall MEP work GL, sector A | 5
137 | erect temp barrier GL, Sector A | 0 | rough in ceiling MEP work GL, sector A | 5
138 | install ext. DDA GL, Sector A | 1 | install interior non-rated partitions GL, Sector A | 5
139 | rough in ceiling MEP work GL, sector A | 6 | finish MEP work GL, sector A | 10
140 | install interior non-rated partitions GL, Sector A | 7 | replace light fixtures 1L, Sector A | 2
141 | finish MEP work GL, sector A | 8 | remove temp barrier GL, Sector A | 2
142 | replace light fixtures 1L, Sector A | 9 | perform patching work as needed GL, Sector A | 2
143 | plaster walls GL, Sector A | 12 | plaster walls GL, Sector A | 2
144 | paint walls GL, Sector A | 13 | paint walls GL, Sector A | 4
145 | install floor finishes GL, Sector A | 14 | install floor finishes GL, Sector A | 4
146 | install ceiling finishes GL, Sector A | 15 | install ceiling finishes GL, Sector A | 4
147 | testing and commissioning GL, Sector A | 16 | testing and commissioning GL, Sector A | 3
148 | Sector A (Lev 1) needs to be after sector b
149 | rough in ceiling MEP work 1L, sector A | 6 | erect temp barrier 1L, Sector A | 3
150 | install interior non-rated partitions, door 1L, Sector A | 7 | remove, salvage column covers 1L, Sector A | 2
151 | finish MEP work 1L, sector A | 8 | demo interior partitions and SDA 1L, Sector A | 2
152 | install equipment, casework 1L, Sector A | 9 | demo all ceilings, salvage lights 1L, Sector A | 2
153 | install side coiling security door 1L, Sector A | 10 | install seismic joints GL, Sector A | 5
154 | erect ceilings 1L, Sector A | 12 | rough in wall MEP work 1L, sector A | 5
155 | replace light fixtures 1L, Sector A | 13 | rough in ceiling MEP work 1L, sector A | 5
156 | create opening at south exterior side of wall 1L, Sector A | 14 | install interior non-rated partitions, door 1L, Sector A | 5
157 | install roll down door with egress 1L, Sector A | 15 | finish MEP work 1L, sector A | 5
158 | remove temp barrier 1L, Sector A | 16 | install equipment, casework 1L, Sector A | 5
159 | perform patching work as needed 1L, Sector A | 17 | install side coiling security door 1L, Sector A | 5
160 | erect temp barrier 1L, Sector A | 0 | reinstall column covers 1L, Sector A | 5
161 | remove, salvage column covers 1L, Sector A | 1 | erect ceilings 1L, Sector A | 5
162 | demo interior partitions and SDA 1L, Sector A | 2 | replace light fixtures 1L, Sector A | 5
163 | demo all ceilings, salvage lights 1L, Sector A | 3 | create opening at south exterior side of wall 1L, Sector A | 2
164 | install seismic joints GL, Sector A | 4 | install roll down door with egress 1L, Sector A | 3
165 | rough in wall MEP work 1L, sector A | 5 | remove temp barrier 1L, Sector A | 2
166 | reinstall column covers 1L, Sector A | 11 | perform patching work as needed 1L, Sector A | 2
167 | Increment 2, Phase 2: Interior Build Out
168 | Sector A (Lev 1)
169 | wait until New Main Connector occupancy 1L, Sector A | 0 | wait until New Main Connector occupancy 1L, Sector A | 0
170 | wait until proposed IMOB occupancy 1L, Sector A | 1 | wait until proposed IMOB occupancy 1L, Sector A | 0
171 | erect temp barrier 1L, Sector A | 2 | erect temp barrier 1L, Sector A | 3
172 | demo 2hr partition and DDA 1L, Sector A | 3 | demo 2hr partition and DDA 1L, Sector A | 2
173 | rough in MEP work GL, sector A | 4 | rough in MEP work GL, sector A | 5
174 | erect interior partitions and SDA 1L, Sector A | 5 | erect interior partitions and SDA 1L, Sector A | 3
175 | finish MEP work GL, sector A | 6 | finish MEP work GL, sector A | 5
176 | install ceilings 1L, Sector A | 7 | install ceilings 1L, Sector A | 3
177 | remove temp barriers 1L, Sector A | 8 | remove temp barriers 1L, Sector A | 2
178 | perform patching work as needed 1L, Sector A | 9 | perform patching work as needed 1L, Sector A | 2
179 | plaster walls 1L, Sector A | 10 | plaster walls 1L, Sector A | 5
180 | paint walls 1L, Sector A | 11 | paint walls 1L, Sector A | 5
181 | install floor finishes 1L, Sector A | 12 | install floor finishes 1L, Sector A | 5
182 | install cieling finsihes 1L, Sector A | 13 | install cieling finsihes 1L, Sector A | 5
183 | testing and commissioning 1L, Sector A | 14 | testing and commissioning 1L, Sector A | 3
184 | Courtyard
185 | install trees Courtyard | 0 | install trees Courtyard | 10
186 | install concrete paving Courtyard | 1 | install concrete paving Courtyard | 6
187 | install light fixtures Courtyard | 3 | protect trees Courtyard | 2
188 | install courtyard furnishings Courtyard | 5 | install light fixtures Courtyard | 5
189 | protect trees Courtyard | 2 | install resin paving Courtyard | 6
190 | install resin paving Courtyard | 4 | install courtyard furnishings Courtyard | 5
0