## TASK
task_code | status_code | wbs_id | end_date | start_date | target_drtn_hr_cnt | task_name | delete_record_flag
Activity ID | Activity Status | WBS Code | (*)Finish | (*)Start | Original Duration(h) | Activity Name | Delete This Row
P1B1000 | Not Started | CEE240F22.Inc01 | 2022-09-01 08:00 | 2022-09-01 08:00 | 0 | NTP
P1B1010 | Not Started | CEE240F22.Inc01 | 2022-09-01 16:00 | 2022-09-01 08:00 | 1 | submit shut down request for facilities
P1B1020 | Not Started | CEE240F22.Inc01 | 2022-09-05 16:00 | 2022-09-02 08:00 | 2 | demo ceilings GL 6.5, M.4
P1B1030 | Not Started | CEE240F22.Inc01 | 2022-11-10 16:00 | 2022-11-08 08:00 | 3 | erect temp barrier, GL 6.5, M.4
P1B1040 | Not Started | CEE240F22.Inc01 | 2022-11-15 16:00 | 2022-11-11 08:00 | 3 | demo exterior walls GL 5.7 M
P1B1050 | Not Started | CEE240F22.Inc01 | 2022-11-18 16:00 | 2022-11-16 08:00 | 3 | demo interior walls GL 5.7 - 7.1 M.4
P1B1060 | Not Started | CEE240F22.Inc01 | 2022-11-21 16:00 | 2022-11-21 08:00 | 1 | remove, salvage column covers, GL 7.1 M
P1B1070 | Not Started | CEE240F22.Inc01 | 2022-09-05 16:00 | 2022-09-02 08:00 | 2 | demo ceilings 1L 7.1, M.4
P1B1080 | Not Started | CEE240F22.Inc01 | 2022-11-24 16:00 | 2022-11-22 08:00 | 3 | remove, dispose 8" san. sewer GL 5.7 D.4
P1B1090 | Not Started | CEE240F22.Inc01 | 2022-09-08 16:00 | 2022-09-06 08:00 | 3 | erect temp barrier 1L M.4
P1B1100 | Not Started | CEE240F22.Inc01 | 2022-09-13 16:00 | 2022-09-09 08:00 | 3 | demo exterior walls 1L 5.7 M
P1B1110 | Not Started | CEE240F22.Inc01 | 2022-09-14 16:00 | 2022-09-14 08:00 | 1 | demo interior walls 1L 6.5 M.4
P1B1120 | Not Started | CEE240F22.Inc01 | 2022-09-19 16:00 | 2022-09-15 08:00 | 3 | remove, salvage column covers, 1L 7.1 M
P1B1130 | Not Started | CEE240F22.Inc01 | 2022-11-24 16:00 | 2022-11-22 08:00 | 3 | remove, dispose 6" forced storm line GL 6.5 D.4 - M.4
P1B1140 | Not Started | CEE240F22.Inc01 | 2022-11-25 16:00 | 2022-11-25 08:00 | 1 | cut and cap 6" storm drain GL 5.7 M.4 - N
P1B1150 | Not Started | CEE240F22.Inc01 | 2022-11-30 16:00 | 2022-11-28 08:00 | 3 | raise ext. conduit into ceiling cavity GL 10.5 B
P1B1160 | Not Started | CEE240F22.Inc01 | 2022-12-01 16:00 | 2022-12-01 08:00 | 1 | verify location of underground utilities sub-GL, Sector B
P1B1170 | Not Started | CEE240F22.Inc01 | 2022-12-05 16:00 | 2022-12-02 08:00 | 2 | demo existing slab as needed sub-GL, Sector B
P1B1180 | Not Started | CEE240F22.Inc01 | 2022-12-07 16:00 | 2022-12-06 08:00 | 2 | excavate soil sub-GL, Sector B
P1B1190 | Not Started | CEE240F22.Inc01 | 2022-12-08 16:00 | 2022-12-08 08:00 | 1 | excavate elevator pit sub-GL, Sector B
P1B1200 | Not Started | CEE240F22.Inc01 | 2022-12-14 16:00 | 2022-12-09 08:00 | 4 | erect shoring, timber lagging sub-GL, Sector B
P1B1210 | Not Started | CEE240F22.Inc01 | 2022-12-20 16:00 | 2022-12-15 08:00 | 4 | install piles sub-GL, Sector B
P1B1220 | Not Started | CEE240F22.Inc01 | 2022-12-30 16:00 | 2022-12-21 08:00 | 8 | formwork, rebar, for pile caps sub-GL, Sector B
P1B1230 | Not Started | CEE240F22.Inc01 | 2023-01-03 16:00 | 2023-01-02 08:00 | 2 | install anchor and bolt connections to moment frame sub-GL, Sector B
P1B1240 | Not Started | CEE240F22.Inc01 | 2023-01-19 16:00 | 2023-01-04 08:00 | 12 | pour concrete, strip formwork for pile caps sub-GL, Sector B
P1B1250 | Not Started | CEE240F22.Inc01 | 2023-01-05 16:00 | 2023-01-04 08:00 | 2 | formwork for footing sub-GL, Sector B
P1B1260 | Not Started | CEE240F22.Inc01 | 2023-01-19 16:00 | 2023-01-06 08:00 | 10 | rebar, pour, strip footings GL, Sector B
P1B1270 | Not Started | CEE240F22.Inc01 | 2023-01-23 16:00 | 2023-01-20 08:00 | 2 | formwork for foundations sub-GL, Sector B
P1B1280 | Not Started | CEE240F22.Inc01 | 2023-01-30 16:00 | 2023-01-24 08:00 | 5 | lay pipes, conduits sub-GL, sector B
P1B1290 | Not Started | CEE240F22.Inc01 | 2023-02-01 16:00 | 2023-01-31 08:00 | 2 | subgrade preparation GL, Sector B
P1B1300 | Not Started | CEE240F22.Inc01 | 2023-02-07 16:00 | 2023-02-02 08:00 | 4 | vapor barrier GL, Sector B
P1B1310 | Not Started | CEE240F22.Inc01 | 2023-02-13 16:00 | 2023-02-08 08:00 | 4 | rebar connecting new foundations to (E) GL, Sector B
P1B1320 | Not Started | CEE240F22.Inc01 | 2023-02-16 16:00 | 2023-02-14 08:00 | 3 | MEP in deck GL, sector B
P1B1330 | Not Started | CEE240F22.Inc01 | 2023-03-02 16:00 | 2023-02-17 08:00 | 10 | rebar, pour, strip foundations GL, Sector B
P1B1340 | Not Started | CEE240F22.Inc01 | 2023-03-08 16:00 | 2023-03-03 08:00 | 4 | erect columns GL, Sector B
P1B1350 | Not Started | CEE240F22.Inc01 | 2023-03-14 16:00 | 2023-03-09 08:00 | 4 | erect beams GL, Sector B
P1B1360 | Not Started | CEE240F22.Inc01 | 2023-03-17 16:00 | 2023-03-15 08:00 | 3 | MEP in deck 1L, sector B
P1B1370 | Not Started | CEE240F22.Inc01 | 2023-03-23 16:00 | 2023-03-20 08:00 | 4 | erect steel deck 1L, Sector B
P1B1380 | Not Started | CEE240F22.Inc01 | 2023-03-29 16:00 | 2023-03-24 08:00 | 4 | erect concrete deck 1L, Sector B
P1B1390 | Not Started | CEE240F22.Inc01 | 2023-04-04 16:00 | 2023-03-30 08:00 | 4 | erect columns 1L, Sector B
P1B1400 | Not Started | CEE240F22.Inc01 | 2023-04-10 16:00 | 2023-04-05 08:00 | 4 | erect beams 1L, Sector B
P1B1410 | Not Started | CEE240F22.Inc01 | 2023-04-13 16:00 | 2023-04-11 08:00 | 3 | MEP in deck 2L, sector B
P1B1420 | Not Started | CEE240F22.Inc01 | 2023-04-19 16:00 | 2023-04-14 08:00 | 4 | erect steel deck 2L, Sector B
P1B1430 | Not Started | CEE240F22.Inc01 | 2023-04-25 16:00 | 2023-04-20 08:00 | 4 | erect concrete deck 2L, Sector B
P1B1440 | Not Started | CEE240F22.Inc01 | 2023-05-01 16:00 | 2023-04-26 08:00 | 4 | erect columns 2L, Sector B
P1B1450 | Not Started | CEE240F22.Inc01 | 2023-05-05 16:00 | 2023-05-02 08:00 | 4 | erect steel deck 3L, Sector B
P1B1460 | Not Started | CEE240F22.Inc01 | 2023-05-26 16:00 | 2023-05-08 08:00 | 15 | curtain wall GL, Sector B
P1B1470 | Not Started | CEE240F22.Inc01 | 2023-05-26 16:00 | 2023-05-08 08:00 | 15 | curtain wall 1L, Sector B
P1B1480 | Not Started | CEE240F22.Inc01 | 2023-05-26 16:00 | 2023-05-08 08:00 | 15 | curtain wall 2L, Sector B
P1B1490 | Not Started | CEE240F22.Inc01 | 2023-05-31 16:00 | 2023-05-29 08:00 | 3 | erect temp barrier, west of new main connector, GL, Sector B
P1B1500 | Not Started | CEE240F22.Inc01 | 2023-05-31 16:00 | 2023-05-29 08:00 | 3 | erect temp barrier, west of new main connector, 1L, Sector B
P1B1510 | Not Started | CEE240F22.Inc01 | 2023-06-05 16:00 | 2023-06-01 08:00 | 3 | erect temp barrier, west of new main connector, 2L, Sector B
P1B1520 | Not Started | CEE240F22.Inc01 | 2023-06-12 16:00 | 2023-06-06 08:00 | 5 | remove roof assembly 2L (E)
P1B1530 | Not Started | CEE240F22.Inc01 | 2023-06-19 16:00 | 2023-06-13 08:00 | 5 | remove parapet, coping 2L (E)
P1B1540 | Not Started | CEE240F22.Inc01 | 2023-06-22 16:00 | 2023-06-20 08:00 | 3 | erect construction barrier 2L (E)
P1B1550 | Not Started | CEE240F22.Inc01 | 2023-06-29 16:00 | 2023-06-23 08:00 | 5 | remove ext window 2L (E)
P1B1560 | Not Started | CEE240F22.Inc01 | 2023-07-06 16:00 | 2023-06-30 08:00 | 5 | demo part of exterior wall 2L (E)
BGL1000 | Not Started | CEE240F22.Inc02.B_LG | 2023-07-11 16:00 | 2023-07-07 08:00 | 3 | erect temp barrier GL, Sector B
BGL1010 | Not Started | CEE240F22.Inc02.B_LG | 2023-07-13 16:00 | 2023-07-12 08:00 | 2 | demo interior barrier GL, Sector B
BGL1020 | Not Started | CEE240F22.Inc02.B_LG | 2023-07-17 16:00 | 2023-07-14 08:00 | 2 | demo DDA GL, Sector B
BGL1030 | Not Started | CEE240F22.Inc02.B_LG | 2023-07-19 16:00 | 2023-07-18 08:00 | 2 | relocate DDA to other side of room GL, Sector B
BGL1040 | Not Started | CEE240F22.Inc02.B_LG | 2023-07-21 16:00 | 2023-07-20 08:00 | 2 | demo ceiling entirely GL, Sector B
BGL1050 | Not Started | CEE240F22.Inc02.B_LG | 2023-07-28 16:00 | 2023-07-24 08:00 | 5 | install seismic joints GL, Sector B
BGL1060 | Not Started | CEE240F22.Inc02.B_LG | 2023-08-04 16:00 | 2023-07-31 08:00 | 5 | erect interior barriers GL, Sector B
BGL1070 | Not Started | CEE240F22.Inc02.B_LG | 2023-08-11 16:00 | 2023-08-07 08:00 | 5 | rough in wall MEP work GL, sector B
BGL1080 | Not Started | CEE240F22.Inc02.B_LG | 2023-08-18 16:00 | 2023-08-14 08:00 | 5 | rough in ceiling MEP work GL, sector B
BGL1090 | Not Started | CEE240F22.Inc02.B_LG | 2023-08-25 16:00 | 2023-08-21 08:00 | 5 | install interior non-rated partitions GL, Sector B
BGL1100 | Not Started | CEE240F22.Inc02.B_LG | 2023-09-08 16:00 | 2023-08-28 08:00 | 10 | finish MEP work GL, sector B
BGL1110 | Not Started | CEE240F22.Inc02.B_LG | 2023-09-15 16:00 | 2023-09-11 08:00 | 5 | install flooring GL, Sector B
BGL1120 | Not Started | CEE240F22.Inc02.B_LG | 2023-09-20 16:00 | 2023-09-18 08:00 | 3 | install SDA GL, Sector B
BGL1130 | Not Started | CEE240F22.Inc02.B_LG | 2023-09-27 16:00 | 2023-09-21 08:00 | 5 | plaster walls GL, Sector B
BGL1140 | Not Started | CEE240F22.Inc02.B_LG | 2023-10-11 16:00 | 2023-09-28 08:00 | 10 | erect ceiling in connector area GL, Sector B
BGL1150 | Not Started | CEE240F22.Inc02.B_LG | 2023-10-25 16:00 | 2023-10-12 08:00 | 10 | install underslung elevator GL, Sector B
BGL1160 | Not Started | CEE240F22.Inc02.B_LG | 2023-10-30 16:00 | 2023-10-26 08:00 | 3 | install column covers in connector area GL, Sector B
BGL1170 | Not Started | CEE240F22.Inc02.B_LG | 2023-11-02 16:00 | 2023-10-31 08:00 | 3 | re-install column covers GL, Sector B
BGL1180 | Not Started | CEE240F22.Inc02.B_LG | 2023-11-07 16:00 | 2023-11-03 08:00 | 3 | re-install roll down door with egress GL, Sector B
BGL1190 | Not Started | CEE240F22.Inc02.B_LG | 2023-11-09 16:00 | 2023-11-08 08:00 | 2 | install doors at storage GL, Sector B
BGL1200 | Not Started | CEE240F22.Inc02.B_LG | 2023-11-13 16:00 | 2023-11-10 08:00 | 2 | remove temp barrier GL, Sector B
BGL1210 | Not Started | CEE240F22.Inc02.B_LG | 2023-11-15 16:00 | 2023-11-14 08:00 | 2 | perform patching work as needed GL, Sector B
BGL1220 | Not Started | CEE240F22.Inc02.B_LG | 2023-11-22 16:00 | 2023-11-16 08:00 | 5 | paint walls GL, Sector B
BGL1230 | Not Started | CEE240F22.Inc02.B_LG | 2023-11-29 16:00 | 2023-11-23 08:00 | 5 | install floor finishes GL, Sector B
BGL1240 | Not Started | CEE240F22.Inc02.B_LG | 2023-12-06 16:00 | 2023-11-30 08:00 | 5 | install ceilings finishes GL, Sector B
BGL1250 | Not Started | CEE240F22.Inc02.B_LG | 2023-12-11 16:00 | 2023-12-07 08:00 | 3 | testing and commissioning GL, Sector B
B1L1000 | Not Started | CEE240F22.Inc02.B_L1 | 2023-07-11 16:00 | 2023-07-07 08:00 | 3 | erect temp barrier 1L, Sector B
B1L1010 | Not Started | CEE240F22.Inc02.B_L1 | 2023-07-25 16:00 | 2023-07-12 08:00 | 10 | erect interim construction tunnel 1L, Sector B
B1L1020 | Not Started | CEE240F22.Inc02.B_L1 | 2023-07-27 16:00 | 2023-07-26 08:00 | 2 | demo interior fire barrier, DDA 1L, Sector B
B1L1030 | Not Started | CEE240F22.Inc02.B_L1 | 2023-07-31 16:00 | 2023-07-28 08:00 | 2 | demo interior partitions 1L, Sector B
B1L1040 | Not Started | CEE240F22.Inc02.B_L1 | 2023-08-07 16:00 | 2023-08-01 08:00 | 5 | install seismic joints 1L, Sector B
B1L1050 | Not Started | CEE240F22.Inc02.B_L1 | 2023-08-08 16:00 | 2023-08-08 08:00 | 1 | remove, salvage door for meditation room 1L, Sector B
B1L1060 | Not Started | CEE240F22.Inc02.B_L1 | 2023-08-09 16:00 | 2023-08-09 08:00 | 1 | remove, salvage column covers 1L, Sector B
B1L1070 | Not Started | CEE240F22.Inc02.B_L1 | 2023-08-16 16:00 | 2023-08-10 08:00 | 5 | rough in wall MEP work 1L, sector B
B1L1080 | Not Started | CEE240F22.Inc02.B_L1 | 2023-08-23 16:00 | 2023-08-17 08:00 | 5 | rough in ceiling MEP work 1L, sector B
B1L1090 | Not Started | CEE240F22.Inc02.B_L1 | 2023-08-30 16:00 | 2023-08-24 08:00 | 5 | install interior partitions 1L, Sector B
B1L1100 | Not Started | CEE240F22.Inc02.B_L1 | 2023-09-06 16:00 | 2023-08-31 08:00 | 5 | install flooring at spec. locations 1L, Sector B
B1L1110 | Not Started | CEE240F22.Inc02.B_L1 | 2023-09-13 16:00 | 2023-09-07 08:00 | 5 | install cieling at spec. locations 1L, Sector B
B1L1120 | Not Started | CEE240F22.Inc02.B_L1 | 2023-09-27 16:00 | 2023-09-14 08:00 | 10 | finish MEP work 1L, sector B
B1L1130 | Not Started | CEE240F22.Inc02.B_L1 | 2023-10-11 16:00 | 2023-09-28 08:00 | 10 | install underslung elevator 1L, Sector B
B1L1140 | Not Started | CEE240F22.Inc02.B_L1 | 2023-10-18 16:00 | 2023-10-12 08:00 | 5 | install column covers in connector area 1L, Sector B
B1L1150 | Not Started | CEE240F22.Inc02.B_L1 | 2023-10-25 16:00 | 2023-10-19 08:00 | 5 | install roll down door with egress 1L, Sector B
B1L1160 | Not Started | CEE240F22.Inc02.B_L1 | 2023-10-26 16:00 | 2023-10-26 08:00 | 1 | replace mediation room door 1L, Sector B
B1L1170 | Not Started | CEE240F22.Inc02.B_L1 | 2023-10-30 16:00 | 2023-10-27 08:00 | 2 | remove temp barriers and tunnel 1L, Sector B
B1L1180 | Not Started | CEE240F22.Inc02.B_L1 | 2023-11-01 16:00 | 2023-10-31 08:00 | 2 | remove temp barrier 1L, Sector B
B1L1190 | Not Started | CEE240F22.Inc02.B_L1 | 2023-11-03 16:00 | 2023-11-02 08:00 | 2 | perform patching work as needed 1L, Sector B
B1L1200 | Not Started | CEE240F22.Inc02.B_L1 | 2023-11-10 16:00 | 2023-11-06 08:00 | 5 | plaster walls 1L, Sector B
B1L1210 | Not Started | CEE240F22.Inc02.B_L1 | 2023-11-17 16:00 | 2023-11-13 08:00 | 5 | paint walls 1L, Sector B
B1L1220 | Not Started | CEE240F22.Inc02.B_L1 | 2023-11-24 16:00 | 2023-11-20 08:00 | 5 | install floor finishes 1L, Sector B
B1L1230 | Not Started | CEE240F22.Inc02.B_L1 | 2023-12-01 16:00 | 2023-11-27 08:00 | 5 | install ceiling finishes 1L, Sector B
B1L1240 | Not Started | CEE240F22.Inc02.B_L1 | 2023-12-06 16:00 | 2023-12-04 08:00 | 3 | testing and commissioning 1L, Sector B
B2L1000 | Not Started | CEE240F22.Inc02.B_L2 | 2023-07-11 16:00 | 2023-07-07 08:00 | 3 | erect int. 2hr partitions 2L, Sector A
B2L1010 | Not Started | CEE240F22.Inc02.B_L2 | 2023-07-14 16:00 | 2023-07-12 08:00 | 3 | erect int. 1hr partitions 2L, Sector A
B2L1020 | Not Started | CEE240F22.Inc02.B_L2 | 2023-07-19 16:00 | 2023-07-17 08:00 | 3 | erect int. non-rated partitions 2L, Sector A
B2L1030 | Not Started | CEE240F22.Inc02.B_L2 | 2023-07-26 16:00 | 2023-07-20 08:00 | 5 | rough in ceiling MEP work 2L, sector A
B2L1040 | Not Started | CEE240F22.Inc02.B_L2 | 2023-08-02 16:00 | 2023-07-27 08:00 | 5 | rough in wall MEP work 2L, sector A
B2L1050 | Not Started | CEE240F22.Inc02.B_L2 | 2023-08-09 16:00 | 2023-08-03 08:00 | 5 | install flooring at spec. locations 2L, Sector A
B2L1060 | Not Started | CEE240F22.Inc02.B_L2 | 2023-08-16 16:00 | 2023-08-10 08:00 | 5 | finish MEP work 2L, sector A
B2L1070 | Not Started | CEE240F22.Inc02.B_L2 | 2023-08-23 16:00 | 2023-08-17 08:00 | 5 | erect ceilings in elevator lobby 2L, Sector A
B2L1080 | Not Started | CEE240F22.Inc02.B_L2 | 2023-09-06 16:00 | 2023-08-24 08:00 | 10 | install underslung elevator 2L, Sector A
B2L1090 | Not Started | CEE240F22.Inc02.B_L2 | 2023-09-13 16:00 | 2023-09-07 08:00 | 5 | install column covers in connector area 2L, Sector A
B2L1100 | Not Started | CEE240F22.Inc02.B_L2 | 2023-09-20 16:00 | 2023-09-14 08:00 | 5 | install DDA between IMOB and elevator 2L, Sector A
B2L1110 | Not Started | CEE240F22.Inc02.B_L2 | 2023-09-22 16:00 | 2023-09-21 08:00 | 2 | remove temp barrier 2L, Sector A
B2L1120 | Not Started | CEE240F22.Inc02.B_L2 | 2023-09-26 16:00 | 2023-09-25 08:00 | 2 | perform patching work as needed 2L, Sector A
B2L1130 | Not Started | CEE240F22.Inc02.B_L2 | 2023-10-03 16:00 | 2023-09-27 08:00 | 5 | plaster walls 2L, Sector A
B2L1140 | Not Started | CEE240F22.Inc02.B_L2 | 2023-10-10 16:00 | 2023-10-04 08:00 | 5 | paint walls 2L, Sector A
B2L1150 | Not Started | CEE240F22.Inc02.B_L2 | 2023-10-17 16:00 | 2023-10-11 08:00 | 5 | install floor finishes 2L, Sector A
B2L1160 | Not Started | CEE240F22.Inc02.B_L2 | 2023-10-24 16:00 | 2023-10-18 08:00 | 5 | install ceiling finishes 2L, Sector A
B2L1170 | Not Started | CEE240F22.Inc02.B_L2 | 2023-10-27 16:00 | 2023-10-25 08:00 | 3 | testing and commissioning 2L, Sector B
AGL1000 | Not Started | CEE240F22.Inc02.A_LG | 2023-07-11 16:00 | 2023-07-07 08:00 | 3 | erect temp barrier GL, Sector A
AGL1010 | Not Started | CEE240F22.Inc02.A_LG | 2023-07-14 16:00 | 2023-07-12 08:00 | 3 | install ext. DDA GL, Sector A
AGL1020 | Not Started | CEE240F22.Inc02.A_LG | 2023-07-19 16:00 | 2023-07-17 08:00 | 3 | demo ext. walls at IMOB connection GL, Sector A
AGL1030 | Not Started | CEE240F22.Inc02.A_LG | 2023-07-24 16:00 | 2023-07-20 08:00 | 3 | demo all ceilings, salvage lights GL, Sector A
AGL1040 | Not Started | CEE240F22.Inc02.A_LG | 2023-07-31 16:00 | 2023-07-25 08:00 | 5 | install seismic joints GL, Sector A
AGL1050 | Not Started | CEE240F22.Inc02.A_LG | 2023-08-07 16:00 | 2023-08-01 08:00 | 5 | rough in wall MEP work GL, sector A
AGL1060 | Not Started | CEE240F22.Inc02.A_LG | 2023-08-14 16:00 | 2023-08-08 08:00 | 5 | rough in ceiling MEP work GL, sector A
AGL1070 | Not Started | CEE240F22.Inc02.A_LG | 2023-08-21 16:00 | 2023-08-15 08:00 | 5 | install interior non-rated partitions GL, Sector A
AGL1080 | Not Started | CEE240F22.Inc02.A_LG | 2023-09-04 16:00 | 2023-08-22 08:00 | 10 | finish MEP work GL, sector A
AGL1090 | Not Started | CEE240F22.Inc02.A_LG | 2023-09-06 16:00 | 2023-09-05 08:00 | 2 | replace light fixtures 1L, Sector A
AGL1100 | Not Started | CEE240F22.Inc02.A_LG | 2023-09-08 16:00 | 2023-09-07 08:00 | 2 | remove temp barrier GL, Sector A
AGL1110 | Not Started | CEE240F22.Inc02.A_LG | 2023-09-12 16:00 | 2023-09-11 08:00 | 2 | perform patching work as needed GL, Sector A
AGL1120 | Not Started | CEE240F22.Inc02.A_LG | 2023-09-14 16:00 | 2023-09-13 08:00 | 2 | plaster walls GL, Sector A
AGL1130 | Not Started | CEE240F22.Inc02.A_LG | 2023-09-20 16:00 | 2023-09-15 08:00 | 4 | paint walls GL, Sector A
AGL1140 | Not Started | CEE240F22.Inc02.A_LG | 2023-09-26 16:00 | 2023-09-21 08:00 | 4 | install floor finishes GL, Sector A
AGL1150 | Not Started | CEE240F22.Inc02.A_LG | 2023-10-02 16:00 | 2023-09-27 08:00 | 4 | install ceiling finishes GL, Sector A
AGL1160 | Not Started | CEE240F22.Inc02.A_LG | 2023-10-05 16:00 | 2023-10-03 08:00 | 3 | testing and commissioning GL, Sector A
A1L1000 | Not Started | CEE240F22.Inc02.A_L1 | 2023-07-11 16:00 | 2023-07-07 08:00 | 3 | erect temp barrier 1L, Sector A
A1L1010 | Not Started | CEE240F22.Inc02.A_L1 | 2023-07-13 16:00 | 2023-07-12 08:00 | 2 | remove, salvage column covers 1L, Sector A
A1L1020 | Not Started | CEE240F22.Inc02.A_L1 | 2023-07-17 16:00 | 2023-07-14 08:00 | 2 | demo interior partitions and SDA 1L, Sector A
A1L1030 | Not Started | CEE240F22.Inc02.A_L1 | 2023-07-19 16:00 | 2023-07-18 08:00 | 2 | demo all ceilings, salvage lights 1L, Sector A
A1L1040 | Not Started | CEE240F22.Inc02.A_L1 | 2023-07-26 16:00 | 2023-07-20 08:00 | 5 | install seismic joints GL, Sector A
A1L1050 | Not Started | CEE240F22.Inc02.A_L1 | 2023-08-02 16:00 | 2023-07-27 08:00 | 5 | rough in wall MEP work 1L, sector A
A1L1060 | Not Started | CEE240F22.Inc02.A_L1 | 2023-08-09 16:00 | 2023-08-03 08:00 | 5 | rough in ceiling MEP work 1L, sector A
A1L1070 | Not Started | CEE240F22.Inc02.A_L1 | 2023-08-16 16:00 | 2023-08-10 08:00 | 5 | install interior non-rated partitions, door 1L, Sector A
A1L1080 | Not Started | CEE240F22.Inc02.A_L1 | 2023-08-23 16:00 | 2023-08-17 08:00 | 5 | finish MEP work 1L, sector A
A1L1090 | Not Started | CEE240F22.Inc02.A_L1 | 2023-08-30 16:00 | 2023-08-24 08:00 | 5 | install equipment, casework 1L, Sector A
A1L1100 | Not Started | CEE240F22.Inc02.A_L1 | 2023-09-06 16:00 | 2023-08-31 08:00 | 5 | install side coiling security door 1L, Sector A
A1L1110 | Not Started | CEE240F22.Inc02.A_L1 | 2023-09-13 16:00 | 2023-09-07 08:00 | 5 | reinstall column covers 1L, Sector A
A1L1120 | Not Started | CEE240F22.Inc02.A_L1 | 2023-09-20 16:00 | 2023-09-14 08:00 | 5 | erect ceilings 1L, Sector A
A1L1130 | Not Started | CEE240F22.Inc02.A_L1 | 2023-09-27 16:00 | 2023-09-21 08:00 | 5 | replace light fixtures 1L, Sector A
A1L1140 | Not Started | CEE240F22.Inc02.A_L1 | 2023-09-29 16:00 | 2023-09-28 08:00 | 2 | create opening at south exterior side of wall 1L, Sector A
A1L1150 | Not Started | CEE240F22.Inc02.A_L1 | 2023-10-04 16:00 | 2023-10-02 08:00 | 3 | install roll down door with egress 1L, Sector A
A1L1160 | Not Started | CEE240F22.Inc02.A_L1 | 2023-10-06 16:00 | 2023-10-05 08:00 | 2 | remove temp barrier 1L, Sector A
A1L1170 | Not Started | CEE240F22.Inc02.A_L1 | 2023-10-10 16:00 | 2023-10-09 08:00 | 2 | perform patching work as needed 1L, Sector A
P2A1L1000 | Not Started | CEE240F22.Inc02.Ph2_A_L1 | 2023-12-07 08:00 | 2023-12-07 08:00 | 0 | wait until New Main Connector occupancy 1L, Sector A
P2A1L1010 | Not Started | CEE240F22.Inc02.Ph2_A_L1 | 2023-10-06 08:00 | 2023-10-06 08:00 | 0 | wait until proposed IMOB occupancy 1L, Sector A
P2A1L1020 | Not Started | CEE240F22.Inc02.Ph2_A_L1 | 2023-12-11 16:00 | 2023-12-07 08:00 | 3 | erect temp barrier 1L, Sector A
P2A1L1030 | Not Started | CEE240F22.Inc02.Ph2_A_L1 | 2023-12-13 16:00 | 2023-12-12 08:00 | 2 | demo 2hr partition and DDA 1L, Sector A
P2A1L1040 | Not Started | CEE240F22.Inc02.Ph2_A_L1 | 2023-12-20 16:00 | 2023-12-14 08:00 | 5 | rough in MEP work GL, sector A
P2A1L1050 | Not Started | CEE240F22.Inc02.Ph2_A_L1 | 2023-12-25 16:00 | 2023-12-21 08:00 | 3 | erect interior partitions and SDA 1L, Sector A
P2A1L1060 | Not Started | CEE240F22.Inc02.Ph2_A_L1 | 2024-01-01 16:00 | 2023-12-26 08:00 | 5 | finish MEP work GL, sector A
P2A1L1070 | Not Started | CEE240F22.Inc02.Ph2_A_L1 | 2024-01-04 16:00 | 2024-01-02 08:00 | 3 | install ceilings 1L, Sector A
P2A1L1080 | Not Started | CEE240F22.Inc02.Ph2_A_L1 | 2024-01-08 16:00 | 2024-01-05 08:00 | 2 | remove temp barriers 1L, Sector A
P2A1L1090 | Not Started | CEE240F22.Inc02.Ph2_A_L1 | 2024-01-10 16:00 | 2024-01-09 08:00 | 2 | perform patching work as needed 1L, Sector A
P2A1L1100 | Not Started | CEE240F22.Inc02.Ph2_A_L1 | 2024-01-17 16:00 | 2024-01-11 08:00 | 5 | plaster walls 1L, Sector A
P2A1L1110 | Not Started | CEE240F22.Inc02.Ph2_A_L1 | 2024-01-24 16:00 | 2024-01-18 08:00 | 5 | paint walls 1L, Sector A
P2A1L1120 | Not Started | CEE240F22.Inc02.Ph2_A_L1 | 2024-01-31 16:00 | 2024-01-25 08:00 | 5 | install floor finishes 1L, Sector A
P2A1L1130 | Not Started | CEE240F22.Inc02.Ph2_A_L1 | 2024-02-07 16:00 | 2024-02-01 08:00 | 5 | install cieling finsihes 1L, Sector A
P2A1L1140 | Not Started | CEE240F22.Inc02.Ph2_A_L1 | 2024-02-12 16:00 | 2024-02-08 08:00 | 3 | testing and commissioning 1L, Sector A
C1000 | Not Started | CEE240F22.Inc02.Courtyard | 2023-11-29 16:00 | 2023-11-16 08:00 | 10 | install trees Courtyard
C1010 | Not Started | CEE240F22.Inc02.Courtyard | 2023-12-07 16:00 | 2023-11-30 08:00 | 6 | install concrete paving Courtyard
C1020 | Not Started | CEE240F22.Inc02.Courtyard | 2023-12-11 16:00 | 2023-12-08 08:00 | 2 | protect trees Courtyard
C1030 | Not Started | CEE240F22.Inc02.Courtyard | 2023-12-18 16:00 | 2023-12-12 08:00 | 5 | install light fixtures Courtyard
C1040 | Not Started | CEE240F22.Inc02.Courtyard | 2023-12-26 16:00 | 2023-12-19 08:00 | 6 | install resin paving Courtyard
C1050 | Not Started | CEE240F22.Inc02.Courtyard | 2024-01-02 16:00 | 2023-12-27 08:00 | 5 | install courtyard furnishings Courtyard

## TASKPRED
pred_task_id | task_id | pred_type | PREDTASK__status_code | TASK__status_code | pred_proj_id | proj_id | predtask__projwbs__wbs_full_name | task__projwbs__wbs_full_name | predtask__task_name | task__task_name | delete_record_flag
Predecessor | Successor | Relationship Type | (*)Predecessor Activity Status | (*)Successor Activity Status | (*)Predecessor Project | (*)Successor Project | (*)Predecessor WBS | (*)Successor WBS | (*)Predecessor Activity Name | (*)Successor Activity Name | Delete This Row
P1B1000 | P1B1010 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | NTP | submit shut down request for facilities
P1B1010 | P1B1020 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | submit shut down request for facilities | demo ceilings GL 6.5, M.4
P1B1020 | P1B1030 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | demo ceilings GL 6.5, M.4 | erect temp barrier, GL 6.5, M.4
P1B1030 | P1B1040 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | erect temp barrier, GL 6.5, M.4 | demo exterior walls GL 5.7 M
P1B1040 | P1B1050 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | demo exterior walls GL 5.7 M | demo interior walls GL 5.7 - 7.1 M.4
P1B1050 | P1B1060 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | demo interior walls GL 5.7 - 7.1 M.4 | remove, salvage column covers, GL 7.1 M
P1B1090 | P1B1100 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | erect temp barrier 1L M.4 | demo exterior walls 1L 5.7 M
P1B1100 | P1B1110 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | demo exterior walls 1L 5.7 M | demo interior walls 1L 6.5 M.4
P1B1120 | P1B1130 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | remove, salvage column covers, 1L 7.1 M | remove, dispose 6" forced storm line GL 6.5 D.4 - M.4
P1B1130 | P1B1140 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | remove, dispose 6" forced storm line GL 6.5 D.4 - M.4 | cut and cap 6" storm drain GL 5.7 M.4 - N
P1B1140 | P1B1150 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | cut and cap 6" storm drain GL 5.7 M.4 - N | raise ext. conduit into ceiling cavity GL 10.5 B
P1B1150 | P1B1160 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | raise ext. conduit into ceiling cavity GL 10.5 B | verify location of underground utilities sub-GL, Sector B
P1B1160 | P1B1170 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | verify location of underground utilities sub-GL, Sector B | demo existing slab as needed sub-GL, Sector B
P1B1170 | P1B1180 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | demo existing slab as needed sub-GL, Sector B | excavate soil sub-GL, Sector B
P1B1180 | P1B1190 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | excavate soil sub-GL, Sector B | excavate elevator pit sub-GL, Sector B
P1B1190 | P1B1200 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | excavate elevator pit sub-GL, Sector B | erect shoring, timber lagging sub-GL, Sector B
P1B1200 | P1B1210 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | erect shoring, timber lagging sub-GL, Sector B | install piles sub-GL, Sector B
P1B1210 | P1B1220 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | install piles sub-GL, Sector B | formwork, rebar, for pile caps sub-GL, Sector B
P1B1220 | P1B1230 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | formwork, rebar, for pile caps sub-GL, Sector B | install anchor and bolt connections to moment frame sub-GL, Sector B
P1B1230 | P1B1240 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | install anchor and bolt connections to moment frame sub-GL, Sector B | pour concrete, strip formwork for pile caps sub-GL, Sector B
P1B1250 | P1B1260 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | formwork for footing sub-GL, Sector B | rebar, pour, strip footings GL, Sector B
P1B1260 | P1B1270 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | rebar, pour, strip footings GL, Sector B | formwork for foundations sub-GL, Sector B
P1B1270 | P1B1280 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | formwork for foundations sub-GL, Sector B | lay pipes, conduits sub-GL, sector B
P1B1280 | P1B1290 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | lay pipes, conduits sub-GL, sector B | subgrade preparation GL, Sector B
P1B1290 | P1B1300 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | subgrade preparation GL, Sector B | vapor barrier GL, Sector B
P1B1300 | P1B1310 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | vapor barrier GL, Sector B | rebar connecting new foundations to (E) GL, Sector B
P1B1310 | P1B1320 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | rebar connecting new foundations to (E) GL, Sector B | MEP in deck GL, sector B
P1B1320 | P1B1330 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | MEP in deck GL, sector B | rebar, pour, strip foundations GL, Sector B
P1B1330 | P1B1340 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | rebar, pour, strip foundations GL, Sector B | erect columns GL, Sector B
P1B1340 | P1B1350 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | erect columns GL, Sector B | erect beams GL, Sector B
P1B1350 | P1B1360 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | erect beams GL, Sector B | MEP in deck 1L, sector B
P1B1360 | P1B1370 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | MEP in deck 1L, sector B | erect steel deck 1L, Sector B
P1B1370 | P1B1380 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | erect steel deck 1L, Sector B | erect concrete deck 1L, Sector B
P1B1380 | P1B1390 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | erect concrete deck 1L, Sector B | erect columns 1L, Sector B
P1B1390 | P1B1400 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | erect columns 1L, Sector B | erect beams 1L, Sector B
P1B1400 | P1B1410 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | erect beams 1L, Sector B | MEP in deck 2L, sector B
P1B1410 | P1B1420 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | MEP in deck 2L, sector B | erect steel deck 2L, Sector B
P1B1420 | P1B1430 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | erect steel deck 2L, Sector B | erect concrete deck 2L, Sector B
P1B1430 | P1B1440 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | erect concrete deck 2L, Sector B | erect columns 2L, Sector B
P1B1440 | P1B1450 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | erect columns 2L, Sector B | erect steel deck 3L, Sector B
P1B1450 | P1B1460 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | erect steel deck 3L, Sector B | curtain wall GL, Sector B
P1B1500 | P1B1510 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | erect temp barrier, west of new main connector, 1L, Sector B | erect temp barrier, west of new main connector, 2L, Sector B
P1B1510 | P1B1520 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | erect temp barrier, west of new main connector, 2L, Sector B | remove roof assembly 2L (E)
P1B1520 | P1B1530 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | remove roof assembly 2L (E) | remove parapet, coping 2L (E)
P1B1530 | P1B1540 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | remove parapet, coping 2L (E) | erect construction barrier 2L (E)
P1B1540 | P1B1550 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | erect construction barrier 2L (E) | remove ext window 2L (E)
P1B1550 | P1B1560 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | remove ext window 2L (E) | demo part of exterior wall 2L (E)
P1B1560 | BGL1000 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc02.B_LG B_LG | demo part of exterior wall 2L (E) | erect temp barrier GL, Sector B
BGL1000 | BGL1010 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | erect temp barrier GL, Sector B | demo interior barrier GL, Sector B
BGL1010 | BGL1020 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | demo interior barrier GL, Sector B | demo DDA GL, Sector B
BGL1020 | BGL1030 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | demo DDA GL, Sector B | relocate DDA to other side of room GL, Sector B
BGL1030 | BGL1040 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | relocate DDA to other side of room GL, Sector B | demo ceiling entirely GL, Sector B
BGL1040 | BGL1050 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | demo ceiling entirely GL, Sector B | install seismic joints GL, Sector B
BGL1050 | BGL1060 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | install seismic joints GL, Sector B | erect interior barriers GL, Sector B
BGL1060 | BGL1070 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | erect interior barriers GL, Sector B | rough in wall MEP work GL, sector B
BGL1070 | BGL1080 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | rough in wall MEP work GL, sector B | rough in ceiling MEP work GL, sector B
BGL1080 | BGL1090 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | rough in ceiling MEP work GL, sector B | install interior non-rated partitions GL, Sector B
BGL1090 | BGL1100 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | install interior non-rated partitions GL, Sector B | finish MEP work GL, sector B
BGL1100 | BGL1110 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | finish MEP work GL, sector B | install flooring GL, Sector B
BGL1110 | BGL1120 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | install flooring GL, Sector B | install SDA GL, Sector B
BGL1120 | BGL1130 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | install SDA GL, Sector B | plaster walls GL, Sector B
BGL1130 | BGL1140 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | plaster walls GL, Sector B | erect ceiling in connector area GL, Sector B
BGL1140 | BGL1150 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | erect ceiling in connector area GL, Sector B | install underslung elevator GL, Sector B
BGL1150 | BGL1160 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | install underslung elevator GL, Sector B | install column covers in connector area GL, Sector B
BGL1160 | BGL1170 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | install column covers in connector area GL, Sector B | re-install column covers GL, Sector B
BGL1170 | BGL1180 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | re-install column covers GL, Sector B | re-install roll down door with egress GL, Sector B
BGL1180 | BGL1190 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | re-install roll down door with egress GL, Sector B | install doors at storage GL, Sector B
BGL1190 | BGL1200 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | install doors at storage GL, Sector B | remove temp barrier GL, Sector B
BGL1200 | BGL1210 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | remove temp barrier GL, Sector B | perform patching work as needed GL, Sector B
BGL1210 | BGL1220 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | perform patching work as needed GL, Sector B | paint walls GL, Sector B
BGL1220 | BGL1230 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | paint walls GL, Sector B | install floor finishes GL, Sector B
BGL1230 | BGL1240 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | install floor finishes GL, Sector B | install ceilings finishes GL, Sector B
BGL1240 | BGL1250 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.B_LG B_LG | install ceilings finishes GL, Sector B | testing and commissioning GL, Sector B
B1L1000 | B1L1010 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | erect temp barrier 1L, Sector B | erect interim construction tunnel 1L, Sector B
B1L1010 | B1L1020 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | erect interim construction tunnel 1L, Sector B | demo interior fire barrier, DDA 1L, Sector B
B1L1020 | B1L1030 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | demo interior fire barrier, DDA 1L, Sector B | demo interior partitions 1L, Sector B
B1L1030 | B1L1040 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | demo interior partitions 1L, Sector B | install seismic joints 1L, Sector B
B1L1040 | B1L1050 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | install seismic joints 1L, Sector B | remove, salvage door for meditation room 1L, Sector B
B1L1050 | B1L1060 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | remove, salvage door for meditation room 1L, Sector B | remove, salvage column covers 1L, Sector B
B1L1060 | B1L1070 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | remove, salvage column covers 1L, Sector B | rough in wall MEP work 1L, sector B
B1L1070 | B1L1080 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | rough in wall MEP work 1L, sector B | rough in ceiling MEP work 1L, sector B
B1L1080 | B1L1090 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | rough in ceiling MEP work 1L, sector B | install interior partitions 1L, Sector B
B1L1090 | B1L1100 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | install interior partitions 1L, Sector B | install flooring at spec. locations 1L, Sector B
B1L1100 | B1L1110 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | install flooring at spec. locations 1L, Sector B | install cieling at spec. locations 1L, Sector B
B1L1110 | B1L1120 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | install cieling at spec. locations 1L, Sector B | finish MEP work 1L, sector B
B1L1120 | B1L1130 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | finish MEP work 1L, sector B | install underslung elevator 1L, Sector B
B1L1130 | B1L1140 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | install underslung elevator 1L, Sector B | install column covers in connector area 1L, Sector B
B1L1140 | B1L1150 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | install column covers in connector area 1L, Sector B | install roll down door with egress 1L, Sector B
B1L1150 | B1L1160 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | install roll down door with egress 1L, Sector B | replace mediation room door 1L, Sector B
B1L1160 | B1L1170 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | replace mediation room door 1L, Sector B | remove temp barriers and tunnel 1L, Sector B
B1L1170 | B1L1180 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | remove temp barriers and tunnel 1L, Sector B | remove temp barrier 1L, Sector B
B1L1180 | B1L1190 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | remove temp barrier 1L, Sector B | perform patching work as needed 1L, Sector B
B1L1190 | B1L1200 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | perform patching work as needed 1L, Sector B | plaster walls 1L, Sector B
B1L1200 | B1L1210 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | plaster walls 1L, Sector B | paint walls 1L, Sector B
B1L1210 | B1L1220 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | paint walls 1L, Sector B | install floor finishes 1L, Sector B
B1L1220 | B1L1230 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | install floor finishes 1L, Sector B | install ceiling finishes 1L, Sector B
B1L1230 | B1L1240 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.B_L1 B_L1 | install ceiling finishes 1L, Sector B | testing and commissioning 1L, Sector B
B2L1000 | B2L1010 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L2 B_L2 | CEE240F22.Inc02.B_L2 B_L2 | erect int. 2hr partitions 2L, Sector A | erect int. 1hr partitions 2L, Sector A
B2L1010 | B2L1020 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L2 B_L2 | CEE240F22.Inc02.B_L2 B_L2 | erect int. 1hr partitions 2L, Sector A | erect int. non-rated partitions 2L, Sector A
B2L1020 | B2L1030 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L2 B_L2 | CEE240F22.Inc02.B_L2 B_L2 | erect int. non-rated partitions 2L, Sector A | rough in ceiling MEP work 2L, sector A
B2L1030 | B2L1040 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L2 B_L2 | CEE240F22.Inc02.B_L2 B_L2 | rough in ceiling MEP work 2L, sector A | rough in wall MEP work 2L, sector A
B2L1040 | B2L1050 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L2 B_L2 | CEE240F22.Inc02.B_L2 B_L2 | rough in wall MEP work 2L, sector A | install flooring at spec. locations 2L, Sector A
B2L1050 | B2L1060 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L2 B_L2 | CEE240F22.Inc02.B_L2 B_L2 | install flooring at spec. locations 2L, Sector A | finish MEP work 2L, sector A
B2L1060 | B2L1070 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L2 B_L2 | CEE240F22.Inc02.B_L2 B_L2 | finish MEP work 2L, sector A | erect ceilings in elevator lobby 2L, Sector A
B2L1070 | B2L1080 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L2 B_L2 | CEE240F22.Inc02.B_L2 B_L2 | erect ceilings in elevator lobby 2L, Sector A | install underslung elevator 2L, Sector A
B2L1080 | B2L1090 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L2 B_L2 | CEE240F22.Inc02.B_L2 B_L2 | install underslung elevator 2L, Sector A | install column covers in connector area 2L, Sector A
B2L1090 | B2L1100 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L2 B_L2 | CEE240F22.Inc02.B_L2 B_L2 | install column covers in connector area 2L, Sector A | install DDA between IMOB and elevator 2L, Sector A
B2L1100 | B2L1110 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L2 B_L2 | CEE240F22.Inc02.B_L2 B_L2 | install DDA between IMOB and elevator 2L, Sector A | remove temp barrier 2L, Sector A
B2L1110 | B2L1120 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L2 B_L2 | CEE240F22.Inc02.B_L2 B_L2 | remove temp barrier 2L, Sector A | perform patching work as needed 2L, Sector A
B2L1120 | B2L1130 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L2 B_L2 | CEE240F22.Inc02.B_L2 B_L2 | perform patching work as needed 2L, Sector A | plaster walls 2L, Sector A
B2L1130 | B2L1140 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L2 B_L2 | CEE240F22.Inc02.B_L2 B_L2 | plaster walls 2L, Sector A | paint walls 2L, Sector A
B2L1140 | B2L1150 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L2 B_L2 | CEE240F22.Inc02.B_L2 B_L2 | paint walls 2L, Sector A | install floor finishes 2L, Sector A
B2L1150 | B2L1160 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L2 B_L2 | CEE240F22.Inc02.B_L2 B_L2 | install floor finishes 2L, Sector A | install ceiling finishes 2L, Sector A
B2L1160 | B2L1170 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L2 B_L2 | CEE240F22.Inc02.B_L2 B_L2 | install ceiling finishes 2L, Sector A | testing and commissioning 2L, Sector B
AGL1000 | AGL1010 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_LG A_LG | CEE240F22.Inc02.A_LG A_LG | erect temp barrier GL, Sector A | install ext. DDA GL, Sector A
AGL1010 | AGL1020 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_LG A_LG | CEE240F22.Inc02.A_LG A_LG | install ext. DDA GL, Sector A | demo ext. walls at IMOB connection GL, Sector A
AGL1020 | AGL1030 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_LG A_LG | CEE240F22.Inc02.A_LG A_LG | demo ext. walls at IMOB connection GL, Sector A | demo all ceilings, salvage lights GL, Sector A
AGL1030 | AGL1040 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_LG A_LG | CEE240F22.Inc02.A_LG A_LG | demo all ceilings, salvage lights GL, Sector A | install seismic joints GL, Sector A
AGL1040 | AGL1050 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_LG A_LG | CEE240F22.Inc02.A_LG A_LG | install seismic joints GL, Sector A | rough in wall MEP work GL, sector A
AGL1050 | AGL1060 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_LG A_LG | CEE240F22.Inc02.A_LG A_LG | rough in wall MEP work GL, sector A | rough in ceiling MEP work GL, sector A
AGL1060 | AGL1070 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_LG A_LG | CEE240F22.Inc02.A_LG A_LG | rough in ceiling MEP work GL, sector A | install interior non-rated partitions GL, Sector A
AGL1070 | AGL1080 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_LG A_LG | CEE240F22.Inc02.A_LG A_LG | install interior non-rated partitions GL, Sector A | finish MEP work GL, sector A
AGL1080 | AGL1090 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_LG A_LG | CEE240F22.Inc02.A_LG A_LG | finish MEP work GL, sector A | replace light fixtures 1L, Sector A
AGL1090 | AGL1100 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_LG A_LG | CEE240F22.Inc02.A_LG A_LG | replace light fixtures 1L, Sector A | remove temp barrier GL, Sector A
AGL1100 | AGL1110 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_LG A_LG | CEE240F22.Inc02.A_LG A_LG | remove temp barrier GL, Sector A | perform patching work as needed GL, Sector A
AGL1110 | AGL1120 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_LG A_LG | CEE240F22.Inc02.A_LG A_LG | perform patching work as needed GL, Sector A | plaster walls GL, Sector A
AGL1120 | AGL1130 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_LG A_LG | CEE240F22.Inc02.A_LG A_LG | plaster walls GL, Sector A | paint walls GL, Sector A
AGL1130 | AGL1140 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_LG A_LG | CEE240F22.Inc02.A_LG A_LG | paint walls GL, Sector A | install floor finishes GL, Sector A
AGL1140 | AGL1150 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_LG A_LG | CEE240F22.Inc02.A_LG A_LG | install floor finishes GL, Sector A | install ceiling finishes GL, Sector A
AGL1150 | AGL1160 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_LG A_LG | CEE240F22.Inc02.A_LG A_LG | install ceiling finishes GL, Sector A | testing and commissioning GL, Sector A
A1L1000 | A1L1010 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_L1 A_L1 | CEE240F22.Inc02.A_L1 A_L1 | erect temp barrier 1L, Sector A | remove, salvage column covers 1L, Sector A
A1L1010 | A1L1020 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_L1 A_L1 | CEE240F22.Inc02.A_L1 A_L1 | remove, salvage column covers 1L, Sector A | demo interior partitions and SDA 1L, Sector A
A1L1020 | A1L1030 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_L1 A_L1 | CEE240F22.Inc02.A_L1 A_L1 | demo interior partitions and SDA 1L, Sector A | demo all ceilings, salvage lights 1L, Sector A
A1L1030 | A1L1040 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_L1 A_L1 | CEE240F22.Inc02.A_L1 A_L1 | demo all ceilings, salvage lights 1L, Sector A | install seismic joints GL, Sector A
A1L1040 | A1L1050 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_L1 A_L1 | CEE240F22.Inc02.A_L1 A_L1 | install seismic joints GL, Sector A | rough in wall MEP work 1L, sector A
A1L1050 | A1L1060 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_L1 A_L1 | CEE240F22.Inc02.A_L1 A_L1 | rough in wall MEP work 1L, sector A | rough in ceiling MEP work 1L, sector A
A1L1060 | A1L1070 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_L1 A_L1 | CEE240F22.Inc02.A_L1 A_L1 | rough in ceiling MEP work 1L, sector A | install interior non-rated partitions, door 1L, Sector A
A1L1070 | A1L1080 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_L1 A_L1 | CEE240F22.Inc02.A_L1 A_L1 | install interior non-rated partitions, door 1L, Sector A | finish MEP work 1L, sector A
A1L1080 | A1L1090 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_L1 A_L1 | CEE240F22.Inc02.A_L1 A_L1 | finish MEP work 1L, sector A | install equipment, casework 1L, Sector A
A1L1090 | A1L1100 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_L1 A_L1 | CEE240F22.Inc02.A_L1 A_L1 | install equipment, casework 1L, Sector A | install side coiling security door 1L, Sector A
A1L1100 | A1L1110 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_L1 A_L1 | CEE240F22.Inc02.A_L1 A_L1 | install side coiling security door 1L, Sector A | reinstall column covers 1L, Sector A
A1L1110 | A1L1120 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_L1 A_L1 | CEE240F22.Inc02.A_L1 A_L1 | reinstall column covers 1L, Sector A | erect ceilings 1L, Sector A
A1L1120 | A1L1130 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_L1 A_L1 | CEE240F22.Inc02.A_L1 A_L1 | erect ceilings 1L, Sector A | replace light fixtures 1L, Sector A
A1L1130 | A1L1140 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_L1 A_L1 | CEE240F22.Inc02.A_L1 A_L1 | replace light fixtures 1L, Sector A | create opening at south exterior side of wall 1L, Sector A
A1L1140 | A1L1150 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_L1 A_L1 | CEE240F22.Inc02.A_L1 A_L1 | create opening at south exterior side of wall 1L, Sector A | install roll down door with egress 1L, Sector A
A1L1150 | A1L1160 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_L1 A_L1 | CEE240F22.Inc02.A_L1 A_L1 | install roll down door with egress 1L, Sector A | remove temp barrier 1L, Sector A
A1L1160 | A1L1170 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_L1 A_L1 | CEE240F22.Inc02.A_L1 A_L1 | remove temp barrier 1L, Sector A | perform patching work as needed 1L, Sector A
P2A1L1010 | P2A1L1020 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | wait until proposed IMOB occupancy 1L, Sector A | erect temp barrier 1L, Sector A
P2A1L1020 | P2A1L1030 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | erect temp barrier 1L, Sector A | demo 2hr partition and DDA 1L, Sector A
P2A1L1030 | P2A1L1040 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | demo 2hr partition and DDA 1L, Sector A | rough in MEP work GL, sector A
P2A1L1040 | P2A1L1050 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | rough in MEP work GL, sector A | erect interior partitions and SDA 1L, Sector A
P2A1L1050 | P2A1L1060 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | erect interior partitions and SDA 1L, Sector A | finish MEP work GL, sector A
P2A1L1060 | P2A1L1070 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | finish MEP work GL, sector A | install ceilings 1L, Sector A
P2A1L1070 | P2A1L1080 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | install ceilings 1L, Sector A | remove temp barriers 1L, Sector A
P2A1L1080 | P2A1L1090 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | remove temp barriers 1L, Sector A | perform patching work as needed 1L, Sector A
P2A1L1090 | P2A1L1100 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | perform patching work as needed 1L, Sector A | plaster walls 1L, Sector A
P2A1L1100 | P2A1L1110 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | plaster walls 1L, Sector A | paint walls 1L, Sector A
P2A1L1110 | P2A1L1120 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | paint walls 1L, Sector A | install floor finishes 1L, Sector A
P2A1L1120 | P2A1L1130 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | install floor finishes 1L, Sector A | install cieling finsihes 1L, Sector A
P2A1L1130 | P2A1L1140 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | install cieling finsihes 1L, Sector A | testing and commissioning 1L, Sector A
C1000 | C1010 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.Courtyard Courtyard | CEE240F22.Inc02.Courtyard Courtyard | install trees Courtyard | install concrete paving Courtyard
C1010 | C1020 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.Courtyard Courtyard | CEE240F22.Inc02.Courtyard Courtyard | install concrete paving Courtyard | protect trees Courtyard
C1020 | C1030 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.Courtyard Courtyard | CEE240F22.Inc02.Courtyard Courtyard | protect trees Courtyard | install light fixtures Courtyard
C1030 | C1040 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.Courtyard Courtyard | CEE240F22.Inc02.Courtyard Courtyard | install light fixtures Courtyard | install resin paving Courtyard
C1040 | C1050 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.Courtyard Courtyard | CEE240F22.Inc02.Courtyard Courtyard | install resin paving Courtyard | install courtyard furnishings Courtyard
P1B1010 | P1B1070 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | submit shut down request for facilities | demo ceilings 1L 7.1, M.4
P1B1060 | P1B1080 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | remove, salvage column covers, GL 7.1 M | remove, dispose 8" san. sewer GL 5.7 D.4
P1B1120 | P1B1080 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | remove, salvage column covers, 1L 7.1 M | remove, dispose 8" san. sewer GL 5.7 D.4
P1B1230 | P1B1250 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | install anchor and bolt connections to moment frame sub-GL, Sector B | formwork for footing sub-GL, Sector B
P1B1260 | P1B1280 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | rebar, pour, strip footings GL, Sector B | lay pipes, conduits sub-GL, sector B
P1B1270 | P1B1290 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | formwork for foundations sub-GL, Sector B | subgrade preparation GL, Sector B
P1B1450 | P1B1470 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | erect steel deck 3L, Sector B | curtain wall 1L, Sector B
P1B1450 | P1B1480 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | erect steel deck 3L, Sector B | curtain wall 2L, Sector B
P1B1460 | P1B1490 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | curtain wall GL, Sector B | erect temp barrier, west of new main connector, GL, Sector B
P1B1470 | P1B1500 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | curtain wall 1L, Sector B | erect temp barrier, west of new main connector, 1L, Sector B
P1B1480 | P1B1510 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | curtain wall 2L, Sector B | erect temp barrier, west of new main connector, 2L, Sector B
P1B1490 | P1B1520 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | erect temp barrier, west of new main connector, GL, Sector B | remove roof assembly 2L (E)
P1B1500 | P1B1520 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | erect temp barrier, west of new main connector, 1L, Sector B | remove roof assembly 2L (E)
P1B1560 | B1L1000 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc02.B_L1 B_L1 | demo part of exterior wall 2L (E) | erect temp barrier 1L, Sector B
P1B1560 | B2L1000 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc02.B_L2 B_L2 | demo part of exterior wall 2L (E) | erect int. 2hr partitions 2L, Sector A
P1B1560 | AGL1000 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc02.A_LG A_LG | demo part of exterior wall 2L (E) | erect temp barrier GL, Sector A
P1B1560 | A1L1000 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc02.A_L1 A_L1 | demo part of exterior wall 2L (E) | erect temp barrier 1L, Sector A
BGL1210 | C1000 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_LG B_LG | CEE240F22.Inc02.Courtyard Courtyard | perform patching work as needed GL, Sector B | install trees Courtyard
B1L1190 | C1000 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.Courtyard Courtyard | perform patching work as needed 1L, Sector B | install trees Courtyard
B2L1120 | C1000 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L2 B_L2 | CEE240F22.Inc02.Courtyard Courtyard | perform patching work as needed 2L, Sector A | install trees Courtyard
AGL1110 | C1000 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_LG A_LG | CEE240F22.Inc02.Courtyard Courtyard | perform patching work as needed GL, Sector A | install trees Courtyard
A1L1170 | C1000 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_L1 A_L1 | CEE240F22.Inc02.Courtyard Courtyard | perform patching work as needed 1L, Sector A | install trees Courtyard
B1L1240 | P2A1L1000 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L1 B_L1 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | testing and commissioning 1L, Sector B | wait until New Main Connector occupancy 1L, Sector A
B2L1170 | P2A1L1000 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.B_L2 B_L2 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | testing and commissioning 2L, Sector B | wait until New Main Connector occupancy 1L, Sector A
AGL1160 | P2A1L1010 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.A_LG A_LG | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | testing and commissioning GL, Sector A | wait until proposed IMOB occupancy 1L, Sector A
P2A1L1000 | P2A1L1020 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | CEE240F22.Inc02.Ph2_A_L1 Ph2_A_L1 | wait until New Main Connector occupancy 1L, Sector A | erect temp barrier 1L, Sector A
P1B1110 | P1B1120 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | demo interior walls 1L 6.5 M.4 | remove, salvage column covers, 1L 7.1 M
P1B1060 | P1B1130 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | remove, salvage column covers, GL 7.1 M | remove, dispose 6" forced storm line GL 6.5 D.4 - M.4
P1B1070 | P1B1090 | FS | Not Started | Not Started | CEE240F22 | CEE240F22 | CEE240F22.Inc01 Increment01 | CEE240F22.Inc01 Increment01 | demo ceilings 1L 7.1, M.4 | erect temp barrier 1L M.4

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Hour ShowAsPercentage=0 SmallScaleQtyType=QT_Hour DateFormat=M/d/yyyy CurrencyFormat=US Dollar